## Plan
Week ending
Stage | Task ID | Task subject | Task detail/notes | Days | Due Date | Completed | 2020-03-20 | 2020-03-27 | 2020-04-03
Design | 1 | Final design | Decide whether to use bootstrap template or create website from scratch | 0.5 | 2020-03-16 | 2020-03-16 | 16/03: Bootstrap template "wine" will be used as the base.
Design | 1.1 | DB schema | Add to Project Plan Doc | 0.5 | 2020-03-19 | 2020-03-17 | 17/03: Created alongside wireframes, 6 tables required
Design | 1.2 | Wireframes | Update existing and add new wireframes | 0.5 | 2020-03-19 | 2020-03-17 | 17/03: Updated existing wireframes. Created wireframes for 11 new pages.
Design | 1.3 | Project Plan Doc | Updated with new pages, wireframes, DB schema, security | 0.5 | 2020-03-20 | 2020-03-17 | 17/03: Completed security section and all required content.
Design | 1.4 | Data | Prepare data and images for the database | 1 | 2020-03-20 | 2020-03-18 | 18/03: Completed data and sourced images.
Development | 2 | Database | Create & populate database | 1 | 2020-03-23 | 2020-03-19 | 19/03: Only add 10 of the 15 cakes to the DB. Left some data for testing | 25/03: Inserted remaining cakes using webpages to test at same time.
Development | 2.1 | CSS & design | Update template to be relevant to requirements. | 3 | 2020-03-27 | 2020-03-27 | 19/03: Create all pages (placeholders) and organise folders etc 20/03: Index, About, Contact, Cakes pages | 21/03: Created admin pages template. 26/03: Review & update responsiveness with unit testing
Development | 2.2 | Develop webpages | Add PHP functionality etc. Including unit testing | 6 | 2020-03-27 | 2020-03-27 |  | 22/03: Completed admin cakes, testimonial, users, company info pages. 23/03: Completed Cakes, cake category pages. 24/03: Single cakes page completed 25/03: Completed update cake page. Updated create cake page to go to cake images page with cake_id created, instead of back to cake list. Removed search function.
Testing | 3.1 | Test Script | Create & complete test scripts | 2 | 2020-04-01 | 2020-04-04 |  | 25/03: Create test scripts
Testing | 3.2 | Functionality | Incl. responsiveness & browser compatibility. Including security | 2 | 2020-04-01 | 2020-04-04 |  | 27/03: Unit testing | 30/03: Responsiveness testing 31/03: Complete testing and screenshots. 01/04: Plesk functionality and testing
Testing | 3.3 | Plesk test | Use free hosting website if plesk unavailable | 0.5 | 2020-04-02 | 2020-04-04 |  |  | 02/04: Testing, mail send working. 03/04: Testing and updates/tweaks. 04/04: Reviewed page formats vs. wireframes and updated as required.
Other | 4.1 | Implementation | Move project to Plesk | 0.5 | 2020-04-02 | 2020-04-01 |  |  | 01/04: Moved database and fields to plesk for testing.
Other | 4.2 | Documentation | Ensure all documentation completed for submission | 0.5 | 2020-04-03 | 2020-04-04 |  |  | 04/04: Review project plan and update as required. Compiled files ready for submission.

## Pages (hidden)
Page | Notes | Status
index |  | Done | * All pages need formatting!
cakes |  | Done
cake_category | Needs email send functionality | Done
single_cake |  | Done
About |  | Done
Contact | Needs email send functionality | WIP
index | Admin login | Done
a_cakes | Admin landing page once logged in | Done | * All pages past here: not logged in = redirect to Admin login page
cake_create |  | Done
cake_update |  | Done
cake_images |  | Done
upload_images |  | Done
delete_images |  | Done
cake_delete | Needs testing | Done
users |  | Done
user_create |  | Done
user_delete |  | Done
coinfo | Need to remove ?id=1 from functionality | Incomplete
testim |  | Done
testim_create |  | Done
testim_delete |  | Done
send_msg
msg_sent | Blank page with thank you message etc
footer |  | Done
logout |  | Done
Navbar | change display and active
Images | add enlarge/zoom option

## Issues (hidden)
Page | Area | Issue | Cause | Solution
Admin index | Login fail | Password not recognised | Password field was only set up for 50 characters | Updated to 255 characters

## Schema
Information required
cake_info |  |  |  | category_option
column | data_type | key | other | column | data_type | key | other
cake_id | INT(11) | PK | NOT NULL AUTO_INCREMENT UNIQUE | cat_id | INT(11) | PK | NOT NULL AUTO_INCREMENT UNIQUE
cat_id | INT(11) | FK | NOT NULL | category | VARCHAR(50) |  | NOT NULL
name | VARCHAR(50) |  | NOT NULL | cat_heading | VARCHAR(100) |  | NOT NULL
cake_desc | VARCHAR (1000) |  | NOT NULL | cat_desc | VARCHAR(1000) |  | NOT NULL
flavours | VARCHAR (200) |  | NOT NULL
icing | VARCHAR (200) |  | NOT NULL
images
column | data_type | key | other
image_id | INT(11) | PK | NOT NULL AUTO_INCREMENT UNIQUE
cake_id | INT(11) | FK | NOT NULL
img_name | VARCHAR(50) |  | NOT NULL
image_desc | VARCHAR(50)
users
column | data_type | key | other
user_id | INT(11) | PK | NOT NULL AUTO_INCREMENT UNIQUE
user_name | VARCHAR(50) |  | NOT NULL
email | VARCHAR(50) |  | NOT NULL UNIQUE
password | VARCHAR(50) |  | NOT NULL
co_info
column | data_type | key | other
info_id | INT(11) | PK | NOT NULL AUTO_INCREMENT UNIQUE
facebook | VARCHAR(200) |  | NOT NULL
instagram | VARCHAR(200) |  | NOT NULL
phone | VARCHAR(20) |  | NOT NULL
co_email | VARCHAR(50) |  | NOT NULL
location | VARCHAR(50) |  | NOT NULL
cakep_heading | VARCHAR(100) |  | NOT NULL
cakep_parag | VARCHAR(2000) |  | NOT NULL
about_heading | VARCHAR(100) |  | NOT NULL
about_desc | VARCHAR(2000) |  | NOT NULL
testimonial
column | data_type | key | other
test_id | INT(11) | PK | NOT NULL AUTO_INCREMENT UNIQUE
test_name | VARCHAR(50) |  | NOT NULL
date | DATETIME |  | NOT NULL
test_desc | VARCHAR(1000) |  | NOT NULL

## Data
cake_info | [5 empty] | users
cake_id | cat_id | name | cake_desc | flavours | icing | user_id | user_name | email | password
1 | 2 | Rainbow | Two tier rainbow panel and smooth pink polka dot with white chocolate drip. Rainbow coloured cake layers also available. | Chocolate, Vanilla, Lemon | Fondant, Chocolate drip | 1 | Penny | pennypicklescakes@gmail.com
2 | 2 | Ironman | Two tier brightly coloured cake with sculpted fondant ironman mask. | Chocolate, Vanilla, Lemon | Fondant
3 | 2 | Unicorn | Two tier angelic unicorn with purple chocolate drip and unicorn horn and ears sculpted from fondant. | Chocolate, Vanilla, Lemon | Buttercream, Chocolate drip
4 | 2 | Piped flowers | Beautiful sparkly bright blue cake with elegantly piped flowers. | Chocolate, Vanilla, Lemon | Buttercream
5 | 2 | Sea Shore | Two tier fondant with seashells and flowers airbrushed with edible paint. | Chocolate, Vanilla, Lemon | Fondant | co_info
6 | 1 | Fresh flowers | Beautiful three tier semi naked wedding cake with edible gold foil and fresh flowers. | Chocolate, Carrot, Lemon & Poppy seed | Buttercream | info_id | facebook | instagram | phone | co_email | location | cakep_heading | cakep_parag | about_heading | about_desc
7 | 1 | Just Married | Three tier drip wedding cake with edible gold foil, adorned with macaroons and fresh flowers. | Chocolate, Vanilla, Carrot, Lemon & Poppy seed | Fondant, Chocolate drip | 1 | https://www.facebook.com/penelope.peirce | https://instagram.com/pennyp18?igshid=gumq1gcky84z | 64275412623 | pennypicklescakes@gmail.com | Hamilton, NZ | Beautiful Cakes for Beautiful Occasions | They taste as wonderful as they look! You can't buy happiness but you can buy cake and that's kind of the same thing... Beautifully Hand-Crafted, One-of-a-Kind, Memorable, Delicious and Stress-Free Cakes for your Special Day. All of our cakes are completely customisable, please use the cakes shown for your inspiration. Prices roughly start at $85 and will vary depending on design and size/servings required. All elements of these cakes including the flavors and designs must be finalised with full payment at least 7 days prior to pickup date. Some designs may be able to be done with less than 7 days notice however, we will not be able to alter any details with less than 7 days notice. Thank you for your understanding. | I sugar coat everything! | Hi I'm Penny, thanks for visiting my website.<br> <br> Cake decorating started as a hobby, making cakes for my family and friends to celebrate their special day. I work full-time in a corporate environment, being able to make these beautiful delicious creations on the side is very rewarding for me. (Yes, I bake and decorate all of the cakes myself)<br> <br> I hope you enjoy browsing my galleries of past work. Whatever you wish for your upcoming occasion, I can design the cake that is right for you.<br> <br> Send through your order, enquiry, or friendly hello via the contact form.
8 | 1 | Calming cream | Three tier ribbed buttercream cake with fresh flowers. | Chocolate, Vanilla, Carrot, Lemon & Poppy seed | Buttercream
9 | 1 | Just White | Two tiers, elegant in all white fondant covered with hand made flowers and piped swirls. | Chocolate, Vanilla, Carrot, Lemon & Poppy seed | Fondant, Buttercream piping
10 | 1 | Caramel Stack | Two tall tiers semi naked smoothed with buttercream and decorated with fresh roses, gold foil and dripped in caramel glaze. | Chocolate, Caramel, Carrot | Buttercream
11 | 3 | Bloom | Two tier gold/chocolate layers with beautifully decorated chocolate panels and an opening white chocolate flower bud. | Chocolate Mud | Buttercream, Chocolate
12 | 3 | Gold Rush | Two tier cake covered in gold coloured icing, gold roses, a bit of sparkle and contrasting white flowers made from fondant. | Chocolate, Vanilla, Lemon | Buttercream, Fondant
13 | 3 | Simply beautiful | Single tier semi naked cake with edible silver foil, pink chocolate drizzle and fresh flowers. | Chocolate, Vanilla, Lemon | Buttercream, Chocolate drip
14 | 3 | Cherry Blossom | Tall single tier with cherry blossom branch and cluster. | Chocolate, Vanilla | Fondant | testimonial
15 | 3 | Vanilla delight | Single tier fluffy vanilla cake layers with a silky buttercream. | Vanilla | Buttercream | test_id | test_name | test_desc | date
[6 empty] | 1 | Susan Boyle | Thank you for our daughter's beautiful cake! I just wanted to say thank you for our daughter's beautiful cake, it looked and tasted amazing, everyone loved the Tom and Jerry theme i think it stole the show. | 2019-10-16
category_option | [5 empty] | 2 | Tom | I just wanted to get in touch to thank you for the incredible cake we received yesterday for our organisations 30th Anniversary. We had so many compliments about the cake and the taste was just perfect. Honestly exceeded our expectations. Thank you all so much. | 2019-08-19
cat_id | category | cat_heading | cat_desc |  |  | 3 | Deborah | Just a quick note to thank you for the fabulous beehive cake that you made for my wife’s 50th birthday. It was everything we wanted and was admired by everyone who came to her party on Saturday. I really appreciate all your help with this. | 2020-01-22
1 | Wedding | Add a personal touch to your wedding day | Wedding cakes are not simply just wedding cakes. They're statements - fashion statements, personality statements, statements of every kind.
2 | Birthday | Every person is unique, why shouldn't their cake be? | A birthday cake is one piece of the party you cannot do without, and blowing out the candles on your birthday cake is an annual rite of passage.
3 | Special Occasion | Special cakes for special occasions! | Important occasions like birthdays, anniversaries and dinner parties call for something special like a beautifully-made cake. A party without cake is really just a meeting.
images
image_id | cake_id | img_name | image_desc
| 1 | rain1
| 1 | rain2
| 2 | iron1
| 2 | iron2
| 3 | unic1
| 3 | unic2
| 4 | bdayflowers1
| 4 | bdayflowers2
| 5 | sea1
| 5 | sea2
| 6 | wedding1
| 6 | wedding2
| 7 | just_m1
| 7 | just_m2
| 8 | rib1
| 8 | rib2
| 9 | white1
| 9 | white2
| 10 | tallwed1
| 10 | tallwed2
| 11 | flower1
| 11 | flower2
| 12 | gold1
| 12 | gold2
| 13 | simple1
| 13 | simple2
| 14 | cherry1
| 14 | cherry2
| 15 | vanilla1
| 15 | vanilla2